## Slide 1: Scope of Work
Notes: Trainer Notes:

## Slide 2: Scope of Work: Objectives
Be able to…
List your contract documents
Know your authority to make changes
Define a Work Character Change
Understand Differing Site Conditions
Notes: Trainer Notes:

## Slide 3: Scope of Work: The Contract
Construct the work described in the Notice to Bidders and as described in the Contract.
CTSS 4-1.03, Work Description
The Plans, Specifications, and other Contract Documents shall govern the work.
GB 2-5, Plans and Specifications
Notes: Trainer Notes:
Scope of work is addressed in Chapter 4 of the CT SS and Chapter 1 Green Book
ASK: What documents make up the contract? (next slide)

## Slide 4: Scope of Work: The Contract
Special Provisions
Project Plans
Revised Standard Specifications
Standard Specifications*
Revised Standard Plans
Standard Plans*
Other?
CTSS Section 5-1.02, Contract Components
GB 2-5.2, Precedence of the Contract Documents
Notes: Trainer Notes:
ASK: What “other” documents are part of the contract?
  Permits
  Executed Change Orders
  Addenda
  Bid/Proposal
Order of precedence (governing ranking) will be addressed in the “Control of Work” module.
The order is different depending which standard specifications you are using: CT 2006, CT 2010, 0r Green Book. Read your contract.
Bidders’ Exchange: website where you/contractor can get copies of the contract docs, including standards and revised standards.

## Slide 5: Scope of Work: The Contract
Intent of plans and specifications:
Contractor:
Furnish the resources to complete the work as described in the Contract.
Where the means and methods to complete the work are not described, choose the means and methods to complete the work.
CTSS 5-1.01, General
GB 2-6, Work to Be Done
Notes: Trainer Notes:
Details for construction = how you must build it = method spec
Details for completion = the finished product = contractor determines the means and methods

## Slide 6: Scope of Work: The Contract
Be as familiar with the work to be done:
    Plans and Specifications
    Commonly accepted practices
    Customs
    Terminology
Notes: Trainer Notes:
Important so:
  The contractor respects you and has confidence in you and your decisions.
  You don’t make mistakes (i.e., in interpretation of contract, in determination of acceptable work, etc.)
ASK: If there is going to be work on your project you are not familiar with what can you do to get familiar with it? (This question is a lead in to the next slide regarding Chap 4 of the CM). Other answers:
  Read your contract docs! Plans and Specs
  Find a job doing similar work and visit it.
  Develop a network of peers you can call (Network this week, join APWA, get to know your local CT RE)
  Bring staff on board that are familiar with the specific work. Consultants?
  Read the Chapter 4 of the CM (next slide)

## Slide 7: Scope of Work: The Contract
Chapter 4, Construction Details, CT CM
Each section in Chapter 4 corresponds to a section in the CTSS
Contains the following four parts:
    General
    Before Work Begins
    During the Course of Work
    Measurement and Payment
Notes: Trainer Notes:
General briefly describes the work covered in the section.
Before Work Begins describes the actions the RE and Assistant RE (inspectors) must take before the contractor begins the construction work.
During the Course of Work describes the actions the RE and Assistant RE must take when the contractor is performing the work.
Measurement and Payment provides guidelines for measuring and paying for the work covered in the section.
So if you needed to inspect Concrete Pipe placement or place Lime Treat Base you could find information in Chapter 4 for each of these.
Does not cover:
  The first nine “General Provisions” sections
  The four “Structures” sections 49, 50, 55, and 59
  Covered in the Bridge Construction Records and Procedures Manual

## Slide 8: Scope of Work: The Contract
Ambiguities and conflicts with plans and specifications:
    Use engineering judgment
    Think about a reasonable contractor’s viewpoint
Notes: Trainer Notes:
When a contract has ambiguities they generally become the problem of the person who wrote the contract when resolving a claim issue.
Avoid searching out and using pure technicalities or making unreasonable inferences.
Consult the design engineer.

## Slide 9: Scope of Work: Changes
The Agency may make changes:
    Within the scope of the work
    Add extra work
    CTSS 4-1.05, Changes and Extra Work
    GB 3, Changes
Notes: Trainer Notes:
CM 3-403, 2010, 2012 Green Book 3.1 & 3.2
Limit changes to those required to complete the work as contemplated at the time the plans and specifications were approved.
Emphasize to the students the importance of keeping changes “within” the scope of the work.
  AKS: Why must you stay within the scope of the work? ‘
  The environmental document evaluated the work as originally scoped, so it only covers that work. Doing work outside the scope would break federal law.
Work that is outside the original scope of the project is not eligible for Federal-aid reimbursement.

## Slide 10: Scope of Work: Changes
Change Order (CO):
  Formal change to the contract.
  Legally binding.
  Details:
    Changed and/or added (extra) work.
    Payment basis.
    Time adjustment.
Notes: Trainer Notes:
If a change must be made, formalize it by executing a change order.
Examples of changes might be:
Increases and decreases in items of work
Eliminating items or portions of work
Changing a specification or construction detail
Adding extra work
Changes requested by the Contractor should be at no cost or reduction in cost to the Agency.

## Slide 11: Scope of Work: Changes
A CO is approved when the Agency signs it.
Extra work performed by the Contactor without an approved CO or written direction from the RE is not paid for.
Change orders will be covered in depth in a later module
CTSS 4-1.05, Changes
GB 3, Changes in Work
Notes: Trainer Notes:
ASK: Is the Contractor required to do CCO work if he does not want to or agree with all parts of the CCO – for example , method of pay? ANSWER: YES.
Exception to Bullet 2: If the engineer needs the contractor to perform CCO work prior to the CCO being written and executed, the engineer must order the work in writing. If this written prior authorization was not provided prior to the contractor performing the work, do not pay for the work.
CCO work performed without prior authorization is not eligible for reimbursement
Note: More about CCOs will be discussed in the CCO module.

## Slide 12: Scope of Work: Work-Character Change
A work-character change has occurred if:
  An ordered plan or spec change materially changes the character of a work item from that on which the bid price was based; and
  The unit cost of the changed item differs when compared to the unit cost of that item under the original plans and specifications; and
  No approved Change Order addresses the payment.
  CTSS 4-1.05B, Work-Character Change
  GB 3-2.2 Contract Unit Prices
Notes: Trainer Notes:
Standard Specifications 4-1.05B; CM 3-403C; Green Book 3.2.2.1
Before work can be considered a work-character change, an ordered change to the plans or specifications must occur.
ASK: What is an ordered change? ANSWER: A CCO or written direction from the Engineer. No order from the engineer, then you can’t have a work-character change.
If such an ordered change materially increases or decreases the unit cost of a bid item, then a work-character change has occurred.
Work-character changes are not to be confused with differing site conditions. (DSC discussed in upcoming slide)

## Slide 13: Scope of Work: Work-Character Change
Bid Item Adjustment = The difference between…
  Force Account Estimated Cost of Performing the work
  per original contract
versus
  Force Account Actual Cost of Performing the work as changed
CM Section 5-306C(2d), Adjustments for Work Character Change
Notes: Trainer Notes:
Adjust the unit price for a bid item if a work-character change occurred.
EMPHASIZE: When calculating the adjustment for a work-character change, the original bid price bears no relation to the adjustment unless it can be demonstrated that the bid price actually represents the cost of the work.
Section 5-3, “Change Orders,” of this manual contains examples of calculations and sample change orders.

## Slide 14: Scope of Work: Differing Site Conditions (DSC)
Type 1: Actual subsurface or latent physical conditions materially different from those indicated or shown in:
      Contract documents
      Job site examination
Examples:
    groundwater where none indicated or reasonable expected
    quantity, strength, and sizes of rocks
    as-built conditions different from the plans
    inaccurate log of test borings
Notes: Trainer Notes:
A differing site condition clause was initially developed by the federal government to protect contractors from excessive risk. The inclusion of the clause benefits Caltrans by reduced bidding contingencies that may be included by contractors. The differing site condition clause is required on all federally funded projects. (23 CFR 635.109)
There are 2 Types of Diff. Site Conditions, the first is …(slide)
Examples of Type 1 conditions that are unknown, shown or not shown in the plans (see slide)
Examples that are not differing site conditions: changes that occur after bidding or contract award such as:
  flooding
  normal water table variations
  landslides
  illegal dumping
  weather-related events

## Slide 15: Scope of Work: Differing Site Conditions (DSC)
Type 2: Unknown physical conditions of an unusual nature that are materially different from those ordinarily encountered and generally recognized as inherent in the work provided for in the contract:
  Examples:
    archaeological finds
    hazardous materials
    endangered species
Notes: Trainer Notes:
Type 2 is frequently claimed when there is no soils report data available for comparative analysis.
ASK: What is the key difference between a Work Character Change and a Differing Site Condition? (next slide)

## Slide 16: Scope of Work: Differing Site Conditions (DSC)
Spec required in all Federal-aid contracts
Protects contractors from excessive risk
Reduces bidding contingencies
23 CFR 635.109
CTSS 4-1.06, Differing Site Conditions
    GB 3-4, Changed Conditions
    LAPM 12.8; CM 3-404
Notes: Trainer Notes:
Read these bullets
Question: Who can give me an example of differing site conditions? Unsuitable subgrade.
DSC are not considered work-character changes because the differing conditions do not result from ordered changes.

## Slide 17: Scope of Work: Differing Site Conditions (DSC)
Contractor notifies RE upon discovery
RE investigates and makes determination
Adjustment warranted
No – Contractor proceeds with work
Yes – Change Order
CTSS 4-1.06, Differing Site Conditions
    GB 3-4, Changed Conditions
    CM 3-404
Notes: Trainer Notes:
Before disturbing the conditions, the contractor must provide to the resident engineer written notice in the form of a request for information.
If Contractor disturbs the site after discovery and before Engineer’s investigation, they waive the differing site condition claim.
Question: Who can give me an example of differing site conditions?
  Unsuitable subgrade
  Sand where Log of Test Boring showed rock.
  Boulders in CIDH hole where cobbles were shown on LOTB
Do not confuse with right of way delay, utilities delay, changes in character and buried man-made objects.

## Slide 18: Scope of Work: Cleanup
Contractor must leave the job site neat and presentable and dispose of:
      Rubbish
      Excess materials
      Falsework
      Temporary structures
      Equipment
      CTSS 4-1.13, Cleanup
      GB 7-8, Work Site Maintenance
Notes: Trainer Notes:
You don’t need to pay the contractor extra work to do this, it is part of the contract.
In addition to this general requirement, Section 22, “Finishing Roadway,” of the Standard Specifications, contains more detailed requirements for cleaning the roadway.
Some construction signs should be left in place until all punch list work is done and final inspection is done. Be sure they are removed prior to contract acceptance.

## Slide 19: Scope of Work Quiz
Notes: Trainer Notes:

## Slide 20: Scope of Work: Quiz
Choose the answer that is not correct.
The following are all parts of the contract:
Standard Plans, COs, Addenda
Contract Plans, Standard Specifications, Permits
Special Provisions, Bid Proposal, Construction Manual
Notes: Trainer Notes:

## Slide 21: Scope of Work: Quiz
Choose the answer that is not correct.
The following are all parts of the contract:
Standard Plans, CCOs, Addenda
Contract Plans, Standard Specifications, Permits
Special Provisions, Bid Proposal, Construction Manual
Notes: Trainer Notes:
The Construction Manual is not part of the contract.

## Slide 22: Scope of Work Quiz
Notes: Trainer Notes:

## Slide 23: Scope of Work: Quiz
True or False:
A Differing Site Condition requires an ordered change from the RE.
Notes: Trainer Notes:

## Slide 24: Scope of Work: Quiz
True or False:
A Differing Site Condition requires an ordered change from the RE.
False: Work-Character Change requires an ordered change from the RE.
Notes: Trainer Notes:

## Slide 25: Scope of Work Quiz
Notes: Trainer Notes:

## Slide 26: Scope of Work: Quiz
True or False:
In order to avoid delay costs, it’s okay for the RE to direct the Contractor verbally to begin CO work.
Notes: Trainer Notes:

## Slide 27: Scope of Work: Quiz
True or False:
In order to avoid delay costs, it’s okay for the RE to direct the Contractor verbally to begin CCO work.
False: Written prior authorization is required.
Notes: Trainer Notes: